## Labour req per day
Phase 1(Procurement Phase 6 months)
Activities | Execution | [15 empty] | Supply
| Pipeline |  | WTP Components Construction | [19 empty] | Activities |  |  | Phase 1 |  | Phase 2 |  | Phase 3
| Trenching | Pipe-laying | Canal Trenching | OHT and GLT Construction | Intake well | Pump house | Clarifier | Chlorinator | Cascade Aerator | Sand filter | water storage tanks | valve fittings | electrical works | Alum mixer | Instrumentation system for SCADA | Washing filter beds | Pipe and fittings un-loading | Site Inspection | Crane Operating | wages | per hour | per day |  |  |  | Skilled | Un-skilled | Skilled | Un-skilled | Skilled | Un-skilled
Skilled | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | skilled | 18 | 144 | Execution | Pipeline | Trenching | 1 | 3 | 5 | 10 | 0 | 0
Total | 13 | [18 empty] | unskilled | 22 | 176 |  |  | Pipe-laying | 1 | 3 | 5 | 10 | 0 | 0
Un-skilled | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  |  |  |  | WTP Components Construction | Canal Trenching | 1 | 3 | 5 | 15 | 0 | 0
Total | 25 | [23 empty] | OHT and GLT Construction | 2 | 3 | 5 | 25 | 2 | 6
[25 empty] | Intake well | 1 | 3 | 5 | 10 | 0 | 0
[25 empty] | Pump house | 1 | 3 | 5 | 10 | 1 | 2
Phase 2(High Mobilization 16 months) | [24 empty] | Clarifier | 0 | 0 | 5 | 10 | 0 | 0
Activities | Execution | [15 empty] | Supply | [7 empty] | Chlorinator | 0 | 0 | 5 | 10 | 0 | 0
| Pipeline |  | WTP Components Construction | [21 empty] | Cascade Aerator | 0 | 0 | 5 | 10 | 0 | 0
| Trenching | Pipe-laying | Canal Trenching | OHT and GLT Construction | Intake well | Pump house | Clarifier | Chlorinator | Cascade Aerator | Sand filter | water storage tanks | valve fittings | electrical works | Alum mixer | Instrumentation system for SCADA | Washing filter beds | Pipe and fittings un-loading | Site Inspection | Crane Operating | [5 empty] | Sand filter | 0 | 0 | 5 | 10 | 0 | 0
Skilled | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 5 | 4 | 2 | 2 | 4 | [5 empty] | water storage tanks | 1 | 2 | 5 | 10 | 0 | 0
Total | 82 | [23 empty] | valve fittings | 0 | 0 | 5 | 10 | 0 | 0
Un-skilled | 10 | 10 | 15 | 25 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 20 | 10 | 10 | 0 | [5 empty] | electrical works | 0 | 0 | 3 | 10 | 0 | 0
Total | 200 | [23 empty] | Alum mixer | 0 | 0 | 2 | 10 | 0 | 0
[25 empty] | Instrumentation system for SCADA | 1 | 0 | 5 | 0 | 2 | 0
[25 empty] | Washing filter beds | 1 | 0 | 4 | 20 | 0 | 0
Phase 3(De-mobilization 2 months) | [22 empty] | Supply |  | Pipe and fittings un-loading | 1 | 5 | 2 | 10 | 0 | 0
Activities | Execution | [15 empty] | Supply | [7 empty] | Site Inspection | 1 | 0 | 2 | 10 | 0 | 0
| Pipeline |  | WTP Components Construction | [21 empty] | Crane Operating | 1 | 0 | 4 | 0 | 1 | 0
| Trenching | Pipe-laying | Canal Trenching | OHT and GLT Construction | Intake well | Pump house | Clarifier | Chlorinator | Cascade Aerator | Sand filter | water storage tanks | valve fittings | electrical works | Alum mixer | Instrumentation system for SCADA | Washing filter beds | Pipe and fittings un-loading | Site Inspection | Crane Operating |  |  |  | Total |  |  | 13 | 25 | 82 | 200 | 6 | 8
Skilled | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1
total | 6
Un-skilled | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 8

## Phase 1 (Model1)
Weekends days-off
Objective Days off |  | 330 |  |  | 1 | days off per week | [6 empty] | 1 | Weekends off per week
[5 empty] | 6 | max work stretch | [6 empty] | 2 | [25 empty] | 1 | min day off in six conecutive days
|  |  | 6 day maximum stretch | [5 empty] | (minimum 1 day off in 6 consecutive days)
[30 empty] | Days off per week |  |  |  |  | Work stretch ends on
Type | Week> | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 1 | 2 | 3 | 4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | [5 empty] | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S
Un-skilled | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 6 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 9 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 13 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 15 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 16 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 17 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 18 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 19 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 20 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 21 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 22 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 23 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 24 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 25 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 26 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 27 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 28 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  | 989184
| 29 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  | 19367936
| 30 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  | 123648
| 31 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 20480768
| 32 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 33 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 34 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 35 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Skilled | 36 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 37 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 38 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 39 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 40 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 41 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 42 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 43 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 44 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 45 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 46 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 48 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 49 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 50 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 51 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 52 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 53 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 54 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 55 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
Available | Type | Workers on duty
35 | 1 | 25 | 29 | 29 | 26 | 31 | 25 | 25 | 25 | 29 | 29 | 26 | 31 | 26 | 26 | 25 | 29 | 29 | 26 | 31 | 27 | 27 | 25 | 29 | 29 | 26 | 31 | 27 | 27
20 | 2 | 13 | 14 | 20 | 18 | 15 | 13 | 13 | 13 | 14 | 20 | 18 | 15 | 17 | 17 | 13 | 14 | 20 | 18 | 15 | 15 | 15 | 13 | 14 | 20 | 18 | 15 | 15 | 15
| Total | 38 | 43 | 49 | 44 | 46 | 38 | 38 | 38 | 43 | 49 | 44 | 46 | 43 | 43 | 38 | 43 | 49 | 44 | 46 | 42 | 42 | 38 | 43 | 49 | 44 | 46 | 42 | 42
Coverage rules:
25 | minimum type 1
13 | minimum type 2
38 | minimum total workers

## P1(Model 2)
[31 empty] | Objective Function |  | 164864
Type | Week> | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [7 empty] | Xij | Week> | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
| Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S |  |  | Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | Shifts per week
Un-skilled | 1 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | Unskilled | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 2 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  |  | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 3 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  |  | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 4 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  |  | 4 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 5 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  |  | 5 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 6 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 6 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 7 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 8 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 8 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 9 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 9 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 10 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 10 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 11 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  |  | 11 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 12 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 12 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 13 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  |  | 13 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 14 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 14 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 3 | 6
| 15 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  |  | 15 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 16 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 16 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 5 | 5 | 6
| 17 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 17 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 3 | 5 | 6
| 18 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  |  | 18 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 5 | 5 | 3 | 5
| 19 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  |  | 19 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 4
| 20 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  |  | 20 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 21 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  |  | 21 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 4
| 22 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 22 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 5 | 5 | 3 | 3
| 23 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  |  | 23 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 4
| 24 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | 24 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 5
| 25 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  |  | 25 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 26 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 26 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 6 | 4 | 6 | 4
| 27 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  |  | 27 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 5 | 3 | 5 | 5
| 28 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  |  | 28 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 5 | 5 | 4 | 4
| 29 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 29 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 5
| 30 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 30 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 4 | 4 | 5
| 31 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 31 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 5 | 3 | 4 | 3
| 32 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 32 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 5 | 5 | 3 | 4
| 33 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  |  | 33 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 5
| 34 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  |  | 34 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 6 | 6 | 4 | 5
| 35 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  |  | 35 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 5 | 5 | 3 | 4
Skilled | 36 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | Skilled | 36 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 37 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  |  | 37 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 3 | 5 | 5 | 5
| 38 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  |  | 38 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 4
| 39 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  |  | 39 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 4 | 5 | 5
| 40 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 |  |  | 40 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 5 | 6 | 4
| 41 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  |  | 41 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 42 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 |  |  | 42 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 5 | 6 | 4
| 43 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  |  | 43 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 5 | 4 | 6
| 44 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  |  | 44 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 3
| 45 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  |  | 45 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 5 | 3 | 5
| 46 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  |  | 46 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5 | 4 | 5 | 3
| 47 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  |  | 47 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 5 | 5 | 3 | 5
| 48 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  |  | 48 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 6 | 6
| 49 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  |  | 49 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | 3
| 50 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  |  | 50 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 51 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  |  | 51 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 5 | 5 | 5
| 52 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  |  | 52 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 4 | 4 | 4
| 53 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  |  | 53 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 3 | 4 | 4 | 4
| 54 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  |  | 54 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 6 | 5 | 4 | 5
| 55 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 |  |  | 55 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 2
[32 empty] | Un-skilled | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
[32 empty] | Skilled | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Labourers required per day
[30 empty] | Unskilled | 25
[30 empty] | Skilled | 13
[18 empty] | Objective Function |  |  | 164864

## Phase 2(Model 1)
Objective Days off |  | 2520 |  |  | 1 | days off per week | [6 empty] | 1 | Weekends off per week
[5 empty] | 6 | max work stretch | [6 empty] | 2 | [25 empty] | 1 | min day off in six conecutive days
|  |  | 6 day maximum stretch | [5 empty] | (minimum 1 day off in 6 consecutive days) | [24 empty] | Weekends days-off
[30 empty] | Days off per week |  |  |  |  | Work stretch ends on
| Week> | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 1 | 2 | 3 | 4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | [5 empty] | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S
Un-skilled | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 10 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 13 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 14 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 17 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 18 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 19 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 20 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 21 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 22 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 23 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 24 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 25 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 26 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 27 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 28 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 29 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 30 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 31 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 32 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 33 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 34 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 36 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 37 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 38 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 39 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 40 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 41 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 42 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 43 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 45 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 46 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 48 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 49 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1
| 50 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 51 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 52 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 53 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 54 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 55 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 56 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 57 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 58 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 59 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 60 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 61 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 63 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 64 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 65 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 66 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 67 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 68 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 69 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 70 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 71 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 72 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 73 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 74 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 75 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 76 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 77 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 78 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 79 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 80 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 81 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 82 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 83 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 84 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 85 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 86 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 87 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 88 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 89 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 90 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 91 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 92 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 93 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 94 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 95 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 97 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 98 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 99 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 100 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 101 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 102 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 103 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 104 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 105 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 106 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 107 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 108 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 109 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 110 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 111 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 112 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 113 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 114 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 115 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 116 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 117 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 118 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 119 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 120 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 121 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 122 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 123 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 124 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 125 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 126 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 127 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 128 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 129 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 130 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 131 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 132 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 133 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 134 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 135 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 136 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 137 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 138 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 139 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 140 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 141 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 142 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 143 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 144 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 145 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 146 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 147 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 148 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 149 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 150 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 151 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 152 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 153 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 154 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 155 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 156 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 157 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 158 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 159 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 160 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 161 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 162 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 163 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 164 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 165 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 166 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 167 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 168 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 169 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 170 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 171 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 172 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 173 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 174 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 175 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 176 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 177 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 178 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 179 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 180 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 181 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 182 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 183 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 184 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 185 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 186 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 187 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 188 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 189 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 190 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 191 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 192 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 193 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 194 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 195 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 196 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 197 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 198 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 199 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 200 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 201 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 202 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 203 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 204 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 205 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 206 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 207 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 208 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 209 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 210 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 211 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 212 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 213 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 214 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 215 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 216 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 217 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 218 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 219 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 220 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 221 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 222 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 223 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 224 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 225 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 226 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 227 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 228 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 229 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 230 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 231 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 232 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 233 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 234 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 235 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 236 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 237 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 238 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 239 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 240 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 241 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 242 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 243 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 244 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 245 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 246 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 247 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 248 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 249 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 250 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 251 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 252 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 253 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 254 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 255 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 256 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 257 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 258 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 259 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 260 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 261 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 262 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 263 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 264 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 265 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 266 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 267 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 268 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 269 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 270 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Skilled | 271 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 272 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 273 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 274 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 275 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 276 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 2
| 277 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 278 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 279 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2
| 280 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2
| 281 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 282 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2
| 283 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 284 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 285 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 286 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 287 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 288 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 289 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 290 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 291 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 292 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2
| 293 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 294 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 295 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 296 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 297 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 298 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 299 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2
| 300 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2
| 301 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1
| 302 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2
| 303 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 304 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 305 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1
| 306 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 2
| 307 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 308 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 309 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2
| 310 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 311 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 312 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 313 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 314 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 315 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1
| 316 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 317 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2
| 318 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 319 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1
| 320 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 321 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 322 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 323 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 324 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 325 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 326 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 327 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 328 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 329 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| 330 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 331 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1
| 332 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1
| 333 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 334 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 335 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1
| 336 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 337 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 338 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 339 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 340 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 341 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 342 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 343 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 344 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 345 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 346 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 347 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 348 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 349 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 350 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2
| 351 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 352 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 353 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 354 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 355 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 356 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 357 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 358 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 359 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 360 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 361 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 362 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 363 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 364 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 365 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 366 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 367 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
| 368 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 369 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 370 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 371 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| 372 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 373 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 374 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 375 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2
| 376 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2
| 377 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 378 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2
| 379 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 380 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 381 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 382 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 383 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2
| 384 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2
| 385 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 386 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1
| 387 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2
| 388 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 389 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 390 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 391 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 392 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 393 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2
| 394 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 395 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2
| 396 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 397 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 398 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2
| 399 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 400 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 401 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1
| 402 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 403 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 404 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 405 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 406 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 407 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 408 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| 409 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 410 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 411 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 412 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 413 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| 414 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 415 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 416 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| 417 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 418 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1
| 419 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2
| 420 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2
Available | Type | Workers on duty
270 | Un-skilled | 200 | 209 | 231 | 217 | 223 | 200 | 200 | 200 | 223 | 231 | 217 | 209 | 200 | 200 | 200 | 221 | 231 | 217 | 211 | 200 | 200 | 201 | 209 | 231 | 217 | 222 | 210 | 210
150 | Skilled | 109 | 108 | 139 | 133 | 111 | 111 | 111 | 110 | 110 | 138 | 133 | 109 | 122 | 122 | 98 | 112 | 140 | 136 | 114 | 108 | 108 | 100 | 118 | 138 | 131 | 113 | 109 | 109
| Total | 110 | 317 | 370 | 350 | 334 | 311 | 311 | 310 | 333 | 369 | 350 | 318 | 322 | 322 | 298 | 333 | 371 | 353 | 325 | 308 | 308 | 301 | 327 | 369 | 348 | 335 | 319 | 319 | [40 empty] | 208.8512 | 216.9583 | 218.1905 | 221.1429 | 234.8571 | 200 | 200 | 206.6607 | 205.625 | 225.5952 | 220.8571 | 241.2619 | 200 | 200 | 200 | 200 | 229.9762 | 226.5238 | 243.5 | 150 | 150 | 215.6607 | 222.625 | 217.8571 | 218.9048 | 224.9524 | 200 | 200
[70 empty] | 112 | 126.5 | 126 | 126.5 | 125 | 82 | 82 | 112 | 126.5 | 126 | 126.5 | 125 | 82 | 82 | 112 | 126.5 | 126 | 126.5 | 125 | 82 | 82 | 112 | 126.5 | 126 | 126.5 | 125 | 82 | 82
[70 empty] | 320.8512 | 343.4583 | 344.1905 | 347.6429 | 359.8571 | 282 | 282 | 318.6607 | 332.125 | 351.5952 | 347.3571 | 366.2619 | 282 | 282 | 312 | 326.5 | 355.9762 | 353.0238 | 368.5 | 232 | 232 | 327.6607 | 349.125 | 343.8571 | 345.4048 | 349.9524 | 282 | 282
Coverage rules:
200 | minimum Un-skilled
82 | minimum Skilled
282 | minimum total workers

## P2(Model 2)
[31 empty] | Objective fun |  | 1210496
| Week> | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [7 empty] | Week> | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
| Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | Xij | Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | Shifts per week
Un-skilled | 1 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | Un-skilled | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 2 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 2 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 3 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 3 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 4 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 4 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 5 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 5 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 6 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 6 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 7 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 7 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 8 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 8 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 9 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 9 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 10 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  | 10 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 11 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 11 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 12 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 12 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 13 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  | 13 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 14 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 14 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 15 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 15 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6 | 1210496
| 16 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 16 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 17 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 17 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 18 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 18 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 19 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 19 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 20 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 20 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 21 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 21 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 22 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 22 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 23 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 23 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 24 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 24 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 25 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 25 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 26 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 26 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 27 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 27 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 28 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 28 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 29 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 29 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 30 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 30 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 31 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 31 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 32 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 32 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 33 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 33 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 34 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 34 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 35 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 35 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 36 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 36 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 37 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 37 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 38 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 38 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 39 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 39 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 40 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 40 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 41 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 41 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 42 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 42 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 43 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 43 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 44 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 44 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 45 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 45 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 46 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 46 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 47 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 47 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 48 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 48 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 49 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 49 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 50 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 50 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 51 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 51 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 52 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 52 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 53 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 53 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 54 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 54 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 55 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 55 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 56 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 56 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 57 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 57 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 58 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 58 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 59 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 59 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 60 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 60 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 61 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 61 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 62 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 62 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 63 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 63 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 64 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 64 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 65 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 65 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 66 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 66 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 67 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  | 67 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 68 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 68 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 69 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 69 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 70 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 70 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 71 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 71 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 72 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 72 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 73 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 73 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 74 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 74 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 75 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 75 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 76 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 76 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 77 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 77 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 78 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 78 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 79 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 79 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 80 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 80 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 81 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 81 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 82 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 82 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 83 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 83 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 84 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 84 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 85 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 85 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 86 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 86 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 87 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 87 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 88 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 88 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 89 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 89 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 90 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 90 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 91 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 91 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 92 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 92 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 93 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 93 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 94 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 94 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 95 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 95 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 96 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 96 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 97 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 97 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 98 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 98 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 99 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 99 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 100 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 100 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 101 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 101 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 102 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 102 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 103 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 103 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 104 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 104 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 105 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 105 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 106 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 106 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 107 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 107 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 108 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 108 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 109 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 109 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 110 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 110 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 111 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 111 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 112 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 112 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 113 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 113 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 114 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 114 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 115 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 115 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 116 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 116 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 117 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 117 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 118 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 118 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 119 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 119 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 120 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 120 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 121 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 121 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 122 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  | 122 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 123 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 123 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 124 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 124 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 125 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 125 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 126 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 126 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 127 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 127 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 128 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 128 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 129 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 129 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 130 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 130 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 131 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 131 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 132 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 132 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 133 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 133 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 134 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 134 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 135 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 135 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 136 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 136 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 137 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 137 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 138 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 138 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 139 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 139 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 140 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 140 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 141 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 141 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 142 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 142 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 143 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 143 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 144 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 145 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 145 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 146 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 146 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 147 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 147 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 148 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 148 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 149 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 149 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 150 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 150 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 151 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 151 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 152 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 152 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 153 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 153 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 154 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 154 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 155 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 155 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 156 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 156 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 157 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 157 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 158 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 158 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 159 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 159 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 160 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 160 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 161 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 161 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 162 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 162 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 163 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 163 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 164 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 164 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 165 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 165 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 166 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 166 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 167 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 167 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 168 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 168 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 169 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 169 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 170 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 170 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 171 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 171 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 172 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 172 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 173 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 173 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 174 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 174 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 175 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 175 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 176 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 176 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 177 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 177 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 4
| 178 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 178 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 179 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 179 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 180 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 180 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 181 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  | 181 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 182 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 |  | 182 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 183 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 183 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 184 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 184 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 185 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 185 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 186 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 186 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 187 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 187 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 188 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 188 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 189 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 189 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 190 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 190 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 191 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 191 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 192 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 192 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 193 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 193 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 194 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 194 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 195 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 195 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 196 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 196 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 197 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 197 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 198 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 198 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 199 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 199 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 200 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 200 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 201 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 201 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 4 | 3
| 202 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 202 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 2 | 3 | 2
| 203 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 203 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 4 | 3 | 5 | 4
| 204 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 |  | 204 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 2
| 205 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 205 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 3 | 2 | 4
| 206 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 206 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 3
| 207 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 207 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 4 | 5
| 208 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 208 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 4 | 1
| 209 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 209 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 5
| 210 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 210 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 1 | 4
| 211 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 211 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 1 | 3 | 3
| 212 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 212 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 4 | 2
| 213 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 213 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 4 | 3 | 4
| 214 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 214 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 4 | 3
| 215 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 215 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 3 | 5 | 2
| 216 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 216 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 2 | 3 | 3
| 217 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 217 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 3 | 5 | 5
| 218 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 218 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 4
| 219 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 219 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 5 | 3 | 4 | 4
| 220 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 220 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 221 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 221 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 5 | 6 | 5
| 222 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 222 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 2 | 4 | 3
| 223 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 223 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 5 | 3 | 3
| 224 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 224 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 3 | 4 | 2
| 225 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 225 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 2 | 4
| 226 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 226 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 5 | 5 | 5
| 227 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 227 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 5 | 3 | 2 | 4
| 228 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 228 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 4
| 229 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 229 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 3 | 5 | 6 | 5
| 230 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 230 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 5 | 3 | 4 | 4
| 231 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 231 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 5 | 6 | 3 | 6
| 232 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 232 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 3 | 5 | 5 | 4
| 233 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 233 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 3 | 4 | 3
| 234 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 234 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 5 | 5 | 3
| 235 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 235 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 4 | 4
| 236 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 236 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 237 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 237 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 4 | 6 | 6 | 4
| 238 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 |  | 238 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 5 | 6 | 3 | 5
| 239 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 239 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 2 | 4 | 4
| 240 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 |  | 240 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 5 | 3 | 3
| 241 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 241 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 5 | 6 | 4 | 3
| 242 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 242 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 4 | 3 | 4 | 4
| 243 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 243 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 5 | 4 | 2
| 244 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 244 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3 | 5 | 5 | 3
| 245 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 245 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 5
| 246 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 246 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 5
| 247 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 247 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 4 | 5 | 4
| 248 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 248 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 5 | 6
| 249 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 |  | 249 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 5 | 6 | 4
| 250 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 250 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | 6 | 6 | 5
| 251 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 |  | 251 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 5 | 5 | 4
| 252 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 252 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 253 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 253 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 5 | 6 | 6
| 254 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 254 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 5 | 6
| 255 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 255 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 256 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 256 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 257 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 |  | 257 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 5 | 6 | 6 | 3
| 258 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 258 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 259 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 259 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 260 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 260 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 261 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 261 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 5 | 3 | 6
| 262 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 262 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 263 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 263 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 264 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 264 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 265 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 |  | 265 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 266 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 266 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 267 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 267 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 268 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 |  | 268 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 269 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 269 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | 4 | 6 | 5
| 270 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  | 270 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | 6 | 4 | 5
Skilled | 271 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | Skilled | 271 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 3 | 3 | 6
| 272 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 272 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 5 | 4 | 4
| 273 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 273 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 5 | 6
| 274 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 274 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 3 | 6
| 275 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 275 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 4 | 4 | 6
| 276 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 |  | 276 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 5 | 4 | 4
| 277 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 277 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 5 | 6 | 4
| 278 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 278 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 6 | 5 | 4 | 6
| 279 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 279 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 5 | 4
| 280 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 280 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 281 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 281 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 282 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 |  | 282 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 283 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 283 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 284 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 284 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 285 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 285 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 286 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 286 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 287 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 287 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 288 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 288 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | 6 | 4 | 6
| 289 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 289 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 290 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 |  | 290 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 5 | 6 | 6 | 3
| 291 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 291 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 292 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 292 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 293 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 293 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 5 | 6 | 4 | 5
| 294 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 294 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 5 | 6 | 6 | 3
| 295 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 295 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 5 | 6 | 4 | 5
| 296 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 296 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 3 | 6 | 6 | 5
| 297 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 297 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 298 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 298 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 299 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 299 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 300 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 300 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 6 | 6 | 6
| 301 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 301 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 6 | 4 | 5
| 302 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 302 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 6 | 6 | 6 | 3
| 303 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 303 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 304 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 304 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 6 | 6 | 5
| 305 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 305 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 306 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 |  | 306 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 6 | 6 | 3
| 307 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 307 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 308 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 308 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 6 | 6 | 5
| 309 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 309 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 4 | 6 | 6 | 6
| 310 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 310 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 4 | 6 | 6 | 2
| 311 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 311 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 312 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 312 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 3 | 6 | 6 | 5
| 313 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 313 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 314 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 314 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5 | 6 | 6 | 3
| 315 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 315 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6 | 4 | 6
| 316 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 316 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 6 | 4 | 6
| 317 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 |  | 317 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 6 | 6 | 3
| 318 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 318 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 5 | 6 | 4 | 5
| 319 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 319 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 6 | 4 | 5
| 320 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 320 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 321 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 321 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 4 | 6 | 4
| 322 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 322 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 4 | 6 | 6
| 323 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 323 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 324 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 324 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 5 | 6 | 6 | 3
| 325 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 325 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 6 | 6 | 5
| 326 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 326 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 6 | 6 | 4 | 6
| 327 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 327 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 6 | 6 | 2
| 328 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 328 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 4 | 6 | 4
| 329 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 329 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 6 | 4 | 5
| 330 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 330 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 6 | 6 | 6
| 331 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 331 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 5 | 6 | 4 | 4
| 332 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 332 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 6 | 6
| 333 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 333 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 6 | 6 | 2
| 334 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 334 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 5 | 6 | 6 | 3
| 335 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 335 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 6 | 4 | 3
| 336 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 336 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 6 | 6 | 3
| 337 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 337 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 6 | 6 | 6 | 4
| 338 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 338 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 5 | 6 | 4 | 4
| 339 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 339 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 5 | 6 | 6 | 2
| 340 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 340 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 6 | 2
| 341 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 341 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 6 | 6 | 4 | 5
| 342 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 342 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 2
| 343 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 343 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 6 | 6 | 3
| 344 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 |  | 344 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 6 | 6 | 3
| 345 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 345 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 5 | 6 | 4 | 5
| 346 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 346 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 6 | 6 | 2
| 347 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 347 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | 6 | 4 | 6
| 348 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 348 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 4 | 2
| 349 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 349 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 6 | 4 | 4
| 350 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 350 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 6 | 6 | 2
| 351 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 351 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 6 | 4 | 3
| 352 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 352 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 3 | 5 | 4
| 353 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 353 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 4
| 354 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 354 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 3 | 2 | 1 | 4
| 355 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 355 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | 1 | 2 | 6
| 356 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 356 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 4
| 357 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 357 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 4 | 1 | 2 | 4
| 358 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 358 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 3 | 1 | 2 | 5
| 359 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 359 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2
| 360 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 360 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5 | 1 | 1 | 5
| 361 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 361 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 2 | 2
| 362 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 362 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 4 | 1 | 3 | 5
| 363 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 363 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 4
| 364 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 364 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 3 | 3 | 1 | 3
| 365 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 365 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 4
| 366 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 366 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 5
| 367 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 367 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 1 | 1 | 3
| 368 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 368 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2
| 369 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 369 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1
| 370 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 370 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 1 | 3
| 371 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 371 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 1 | 4 | 3
| 372 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 372 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 3 | 1 | 1 | 3
| 373 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 373 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 3
| 374 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 374 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2
| 375 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 375 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 3 | 1
| 376 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 376 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 1
| 377 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 377 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 | 3 | 2 | 3
| 378 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 378 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 379 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 379 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 1 | 3
| 380 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 380 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 1 | 4 | 4
| 381 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 381 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 382 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 382 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 2
| 383 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 383 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 1 | 1 | 2
| 384 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 384 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 1
| 385 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 385 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 4 | 2 | 2 | 4
| 386 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 386 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 387 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 387 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 4
| 388 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 388 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 3 | 2
| 389 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 389 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 4 | 2 | 1 | 4
| 390 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 390 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 4 | 2 | 1 | 3
| 391 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 391 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 3
| 392 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 392 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 4 | 1 | 3 | 3
| 393 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 393 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4
| 394 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 394 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 2 | 3 | 2
| 395 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 395 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 2
| 396 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 396 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 5 | 1 | 1 | 5
| 397 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 397 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 3 | 2 | 5 | 4
| 398 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 398 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 4 | 5
| 399 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 399 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 2 | 1 | 3
| 400 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 400 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 5 | 2 | 2 | 4
| 401 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 |  | 401 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 4 | 3 | 1 | 3
| 402 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 402 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 2 | 1
| 403 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 403 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 404 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 |  | 404 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 4 | 5
| 405 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 405 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 3 | 1 | 2 | 4
| 406 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 406 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 4
| 407 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 407 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 3 | 3 | 3
| 408 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 408 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 2 | 1 | 4
| 409 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 |  | 409 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1
| 410 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 410 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 4 | 1 | 2 | 4
| 411 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 411 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 4 | 4 | 3
| 412 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 412 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 4 | 4 | 2
| 413 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 413 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 4 | 2 | 6 | 3
| 414 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 414 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 3 | 2 | 2
| 415 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 |  | 415 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 3 | 5 | 3
| 416 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 |  | 416 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 2 | 5 | 2
| 417 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 417 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 5 | 2
| 418 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 418 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 2
| 419 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 |  | 419 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 5 | 4 | 4 | 4
| 420 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  | 420 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 3 | 2 | 3 | 4
[31 empty] | Un-skilled | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
[31 empty] | Skilled | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82 | 82
Labourers required per day
[30 empty] | Unskilled | 200
[30 empty] | Skilled | 82

## Phase 3(Model 1)
Weekends days-off
Objective Days off |  | 300 |  |  | 1 | days off per week | [6 empty] | 1 | Weekends off per week
[5 empty] | 6 | max work stretch | [6 empty] | 2 | [25 empty] | 1 | min day off in six conecutive days
|  |  | 6 day maximum stretch | [5 empty] | (minimum 1 day off in 6 consecutive days)
[30 empty] | Days off per week |  |  |  |  | Work stretch ends on
| Week> | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 2 | 3 | 4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | [5 empty] | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S
Un-skilled | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 9 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 10 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 12 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 13 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 14 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 15 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 16 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 18 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 19 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 20 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 21 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 22 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 23 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 24 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 25 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 26 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 27 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 28 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 29 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 30 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Type 2 | 31 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 32 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 34 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 35 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 36 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 37 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 38 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 39 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 40 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 41 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 42 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 43 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 44 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 45 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 46 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 47 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 48 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 49 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 50 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Available | Type | Workers on duty
30 | Unskilled | 13 | 28 | 28 | 29 | 22 | 20 | 20 | 13 | 28 | 28 | 29 | 22 | 22 | 22 | 13 | 28 | 28 | 29 | 22 | 22 | 22 | 13 | 28 | 28 | 29 | 22 | 26 | 26
20 | Skilled | 8 | 16 | 20 | 18 | 18 | 16 | 16 | 8 | 16 | 20 | 18 | 18 | 16 | 16 | 8 | 16 | 20 | 18 | 18 | 12 | 12 | 8 | 16 | 20 | 18 | 18 | 16 | 16
| Total | 21 | 44 | 48 | 47 | 40 | 36 | 36 | 21 | 44 | 48 | 47 | 40 | 38 | 38 | 21 | 44 | 48 | 47 | 40 | 34 | 34 | 21 | 44 | 48 | 47 | 40 | 42 | 42
Coverage rules:
8 | minimum type 1
6 | minimum type 2
14 | minimum total workers

## P3(Model 2)
|  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
| Day> | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S
Type 1 | 1 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
| 2 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | [5 empty] | Xij | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S
| 3 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 |  |  |  |  | Un-skilled | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| 4 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | [5 empty] | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| 5 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | [5 empty] | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
| 6 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| 7 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | [5 empty] | 5 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 8 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 10000 | 10000 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | [5 empty] | 6 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 9 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | [5 empty] | 7 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 10 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | [5 empty] | 8 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
| 11 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 9 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | [5 empty] | 10 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 12 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 15 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | [5 empty] | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 16 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 14 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 17 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | [5 empty] | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 18 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 10000 | 10000 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | [5 empty] | 16 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
| 19 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | [5 empty] | 17 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 20 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | [5 empty] | 18 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 21 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 19 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 22 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 20 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 23 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 21 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 24 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 10000 | 10000 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 25 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 23 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 26 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 24 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 27 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 25 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 28 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 26 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 29 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 27 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| 30 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 10000 | 10000 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | 10000 | 144 | 144 | 144 | 144 | 144 | 144 | [5 empty] | 28 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Type 2 | 31 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 29 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 32 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | [5 empty] | 30 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
| 33 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 |  |  |  |  | Skilled | 31 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 34 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | [5 empty] | 32 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 35 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 36 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1
| 37 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 35 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0
| 38 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | [5 empty] | 36 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 39 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 37 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1
| 40 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | [5 empty] | 38 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 41 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 39 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| 42 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 10000 | 10000 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | [5 empty] | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
| 43 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | [5 empty] | 41 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0
| 44 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 42 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1
| 45 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 43 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
| 46 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | [5 empty] | 44 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| 47 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 45 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 48 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 10000 | 10000 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 46 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| 49 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 47 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| 50 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 10000 | 10000 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | 10000 | 176 | 176 | 176 | 176 | 176 | 176 | [5 empty] | 48 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
[35 empty] | 49 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0
| Objective function |  |  | 61824 | [30 empty] | 50 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0
|  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
| Xij | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | M | T | W | R | F | s | S | Shifts per week
Un-skilled | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 3 | 4 | 5
| 2 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 4 | 3 | 4 | 5
| 3 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 6 | 3 | 6 | 5
| 4 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | 3 | 5 | 5
| 5 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 4 | 6 | 4 | 3
| 6 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 5 | 4 | 5 | 5
| 7 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 2
| 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 13 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 14 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 20 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 21 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 22 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1
| 23 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 1 | 1
| 24 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 1 | 3
| 25 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1
| 26 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2
| 27 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1
| 28 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 1 | 1
| 29 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 1
| 30 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Skilled | 31 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 6 | 5 | 5
| 32 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 5 | 3 | 5 | 3
| 33 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 5 | 4 | 4 | 5
| 34 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 4 | 2 | 6 | 5
| 35 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | 3 | 4 | 6
| 36 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 2 | 2 | 3
| 37 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 38 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1
| 39 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1
| 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 41 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 42 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1
| 43 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| 44 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 2 | 1
| 45 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1
| 46 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1
| 47 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 1
| 48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1
| 49 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 2
| 50 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 1
| Unskilled | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Skilled | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Labourers required per day
| Unskilled | 8
| Skilled | 6